## data-entry
Date | level-1 | level-2 | size-delta | release-target | work-completed
2020-03-02 | getting-started | ionic-info | 0.5 | 0.5 | 0
2020-03-02 | getting-started | mob-programming | 0.5 | 0.5 | 0
2020-03-02 | getting-started | research-bracket | 0.5 | 0.5 | 0
2020-03-02 | getting-started | excel-data-expirment | 4 | 4 | 0
2020-03-02 | pages-nav | qr-expirment | 1 | 1 | 0
2020-03-02 | pages-nav | join-tourney | 1 | 1 | 0
2020-03-02 | pages-nav | confirm-game-result | 3 | 3 | 0
2020-03-02 | pages-nav | real-home-page | 2 | 2 | 0
2020-03-02 | pages-nav | fraud-prevention | 2 | 2 | 0
2020-03-02 | pages-nav | submit-result-status | 1 | 1 | 0
2020-03-02 | pages-nav | setup-game | 1 | 1 | 0
2020-03-02 | pages-nav | game-scoring-page | 3 | 3 | 0
2020-03-02 | stats | win-and-losses | 1 | 1 | 0
2020-03-02 | stats | points-breakdown | 3 | 3 | 0
2020-03-02 | stats | tourney-stats | 1 | 1 | 0
2020-03-02 | stats | booby-prize-most-klasks | 0.5 | 0.5 | 0
2020-03-02 | admin | admin-login | 1 | 1 | 0
2020-03-02 | admin | create-tourney | 0.5 | 0.5 | 0
2020-03-02 | admin | qr-poster | 1 | 1 | 0
2020-03-02 | deploy | web-pwa | 1 | 1 | 0
2020-03-02 | deploy | ios | 3 | 3 | 0
2020-03-02 | deploy | android | 1.5 | 1.5 | 0
2020-03-02 | misc | choose-db | 3 | 3 | 0
2020-03-02 | misc | css-aesthetics | 3 | 3 | 0
2020-03-02 | misc | tourney-recruiting | 0.5 | 0.5 | 0
2020-03-11 | getting-started | research-bracket | -0.5 | 0 | 0.5
2020-03-11 | getting-started | excel-data-expirment | -3 | 0 | 3
2020-03-12 | getting-started | ionic-info | -0.5 | 0 | 0.5
2020-03-12 | getting-started | mob-programming | -0.5 | 0 | 0.5
2020-03-12 | getting-started | excel-data-expirment | -1 | 0 | 1
2020-04-13 | misc | choose-db | -3 | 0 | 3
2020-04-13 | misc | web-api | 2 | 2 | 0
2020-04-13 | deploy | ios | -3 | -3 | 0
2020-04-13 | deploy | android | -1.5 | -1.5 | 0
2020-04-13 | misc | tourney-recruiting | -0.5 | -0.5 | 0
2020-04-13 | admin | qr-poster | -1 | -1 | 0
2020-04-15 | stats | win-and-losses | -1 | 0 | 1
2020-04-15 | stats | booby-prize-most-klasks | 0.5 | 0.5 | 0

## backlog-breakdown
backlog-breakdown | date
work-buckets | 2020-03-02 | 2020-03-11 | 2020-03-12 | 2020-04-13 | 2020-04-15 | total
getting-started | 5.5 | -3.5 | -2 |  |  | 0
pages-nav | 14 |  |  |  |  | 14
confirm-game-result | 3 |  |  |  |  | 3
fraud-prevention | 2 |  |  |  |  | 2
game-scoring-page | 3 |  |  |  |  | 3
join-tourney | 1 |  |  |  |  | 1
qr-expirment | 1 |  |  |  |  | 1
real-home-page | 2 |  |  |  |  | 2
setup-game | 1 |  |  |  |  | 1
submit-result-status | 1 |  |  |  |  | 1
stats | 5.5 |  |  |  | -0.5 | 5
win-and-losses | 1 |  |  |  | -1 | 0
points-breakdown | 3 |  |  |  |  | 3
tourney-stats | 1 |  |  |  |  | 1
booby-prize-most-klasks | 0.5 |  |  |  | 0.5 | 1
admin | 2.5 |  |  | -1 |  | 1.5
deploy | 5.5 |  |  | -4.5 |  | 1
misc | 6.5 |  |  | -1.5 |  | 5
total | 39.5 | -3.5 | -2 | -7 | -0.5 | 26.5

## burn-up
Row Labels | Sum of release-target | Sum of work-completed | date | release-target | work-completed
2020-03-02 | 39.5 | 0 | 2020-03-02 | 39.5 | 0
2020-03-11 | 39.5 | 3.5 | 2020-03-11 | 39.5 | 3.5
2020-03-12 | 39.5 | 5.5 | 2020-03-12 | 39.5 | 5.5
2020-04-13 | 35.5 | 8.5 | 2020-04-13 | 35.5 | 8.5
2020-04-15 | 36 | 9.5 | 2020-04-15 | 36 | 9.5
|  |  | 2020-07-01 | 36
Formulas:
date = [Row Labels]